## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Light
PROJECT:CAR PURCHASE 0845536
| Contoso, Ltd. | [7 empty] | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Class Project Assignment
| Project start date: | 2023-09-13 | [7 empty] | September | [20 empty] | October | [27 empty] | November
| Scrolling increment: | 0 | time axis 2023-09-13 to 2023-11-07
WBS | Milestone description | Category | Assigned to | Number of People | Duration(min) | Cost | Progress | Start | Days | time axis 2023-09-13 to 2023-11-07
1 | Project charter
2 | Concept Matrix | Goal | All Team | 5 | 30 | 75 | 100% | 2023-09-13 | 1 | 2023-09-13: 2
2.1 | Select team | Goal | All Team | 5 | 5 | 12.5 | 100% | 2023-09-13 | 1 | 2023-09-13: 2
2.2 | Rough out Concept matrix | Goal | All Team | 5 | 25 | 62.5 | 100% | 2023-09-13 | 1 | 2023-09-13: 2
3 | Determine Teams For Search | Milestone | KISHVAR KISHVAR | 1 | 8 | 4 | 100% | 2023-09-26 | 1 | bar: 2023-09-26
3.1.1 | Porsche Boxster | Goal | Team 1 | 1 | 1 | 0.5 | 100% | 2023-09-26 | 1 | 2023-09-26: 2
3.1.2 | Fiat Spyder | Goal | Team 2 | 1 | 1 | 0.5 | 100% | 2023-09-26 | 1 | 2023-09-26: 2
3.1.3 | Viper | Goal | Team 3 | 1 | 1 | 0.5 | 100% | 2023-09-26 | 1 | 2023-09-26: 2
3.1.4 | Corvette | Goal | Team 4 | 1 | 1 | 0.5 | 100% | 2023-09-26 | 1 | 2023-09-26: 2
3.1.5 | Lambo Gallarda | Goal | Team 5 | 1 | 1 | 0.5 | 100% | 2023-09-26 | 1 | 2023-09-26: 2
3.1.6 | Audi TT | Goal | Team 6 | 1 | 1 | 0.5 | 100% | 2023-09-26 | 1 | 2023-09-26: 2
3.1.7 | BMW Z3 Roadster | Goal | Team 7 | 1 | 1 | 0.5 | 100% | 2023-09-26 | 1 | 2023-09-26: 2
3.1.8 | Mazda Miata/MX5 | Goal | Team 8 | 1 | 1 | 0.5 | 100% | 2023-09-26 | 1 | 2023-09-26: 2
4 | Teams Complete Vehicle Search using Sources | Milestone | Teams | 3 |  | 0 | 100% | 2023-09-26 | 1 | bar: 2023-09-26
4.1 | FB Marketplace | Goal |  | 3 | 0 | 0 | 100% | 2023-09-26 | 1 | 2023-09-26: 2
4.1 | Autotrader | Goal |  | 3 | 0 | 0 | 100% | 2023-09-26 | 1 | 2023-09-26: 2
4.1 | Carguru | Goal |  | 3 | 0 | 0 | 100% | 2023-09-26 | 1 | 2023-09-26: 2
4.1 | Porsche Boxster | Goal | Team 1 | 3 | 45 | 67.5 | 100% | 2023-09-26 | 1 | 2023-09-26: 2
4.1 | Fiat Spyder | Goal | Team 2 | 3 | 50 | 75 | 100% | 2023-09-26 | 1 | 2023-09-26: 2
4.1 | Viper | Goal | Team 3 | 3 | 20 | 30 | 100% | 2023-09-26 | 1 | 2023-09-26: 2
4.1 | Corvette | Goal | Team 4 | 3 | 30 | 45 | 100% | 2023-09-26 | 1 | 2023-09-26: 2
4.1 | Lambo Gallarda | Goal | Team 5 | 3 | 60 | 90 | 100% | 2023-09-26 | 1 | 2023-09-26: 2
4.1 | Audi TT | Goal | Team 6 | 3 | 60 | 90 | 100% | 2023-09-26 | 1 | 2023-09-26: 2
4.1 | BMW Z3 Roadster | Goal | Team 7 | 3 | 60 | 90 | 100% | 2023-09-26 | 1 | 2023-09-26: 2
4.1 | Mazda Miata/MX5 | Goal | Team 8 | 3 | 60 | 90 | 100% | 2023-09-26 | 1 | 2023-09-26: 2
5 | Spreadsheet Criteria | Milestone | All | 10 | 25 | 125 | 100% | 2023-09-26 | 1 | bar: 2023-09-26
5.1 | Assign Values | Goal | All |  | 24 | 0 | 100% | 2023-09-26 | 1 | 2023-09-26: 2
5.2 | Calculate Values | Goal | All |  | 1 | 0 | 100% | 2023-09-26 | 1 | 2023-09-26: 2
6 | Top 5 Vehicles | Milestone | All | 10 | 5 | 25 | 100% | 2023-09-26 | 1 | bar: 2023-09-26
7 | Arrange Road Tests | Milestone | See Team Assignments | 2 | 2 | 2 | 5% | ECD 10/3/2023
7.1 | Lambo | Goal | Drive Team 1 | 2 |  | 0 | 5% | ECD 10/3/2023
7.1.1 | Set up appointment | Goal | Drive Team 1 | 1 | 10 | 5 | 5% | ECD 10/3/2023
7.1.2 | Go to the place to do the road test | Goal | Drive Team 1 | 1 | 10 | 5 | 5% | ECD 10/3/2023
7.1.3 | Assessment of vehicle while driving | Goal | Drive Team 1 | 1 | 30 | 15 | 5% | ECD 10/3/2023
7.1.4 | Check Reliability Info (CARFAX) | Goal | Drive Team 1 | 1 | 30 | 15 | 5% | ECD 10/3/2023
7.1.5 | Get Home | Goal | Drive Team 1 | 2 | 10 | 10 | 5% | ECD 10/3/2023
7.2 | BMW Z3 Roadster (2) | Goal | Drive Team 2 | 2 |  | 0 | 5% | ECD 10/3/2023
7.2.1 | Set up appointment | Goal | Drive Team 2 | 1 | 5 | 2.5 | 5% | ECD 10/3/2023
7.2.2 | Go to the place to do the road test | Goal | Drive Team 2 | 1 | 5 | 2.5 | 5% | ECD 10/3/2023
7.2.3 | Assessment of vehicle while driving | Goal | Drive Team 2 | 1 | 20 | 10 | 5% | ECD 10/3/2023
7.2.4 | Check Reliability Info (CARFAX) | Goal | Drive Team 2 | 1 | 20 | 10 | 5% | ECD 10/3/2023
7.2.5 | Get Home | Goal | Drive Team 2 | 2 | 5 | 5 | 5% | ECD 10/3/2023
7.3 | Boxster / Audi | Goal | 1/2 of Drive Team 1 & 2 | 2 |  | 0 | 5% | ECD 10/7/2023
7.3.1 | Set up appointment | Goal | 1/2 of Drive Team 1 & 2 | 1 | 5 | 2.5 | 5% | ECD 10/7/2023
7.3.2 | Go to the place to do the road test | Goal | 1/2 of Drive Team 1 & 2 | 1 | 5 | 2.5 | 5% | ECD 10/7/2023
7.3.3 | Assessment of vehicle while driving | Goal | 1/2 of Drive Team 1 & 2 | 1 | 20 | 10 | 5% | ECD 10/7/2023
7.3.4 | Check Reliability Info (CARFAX) | Goal | 1/2 of Drive Team 1 & 2 | 1 | 20 | 10 | 5% | ECD 10/7/2023
7.3.5 | Get Home | Goal | 1/2 of Drive Team 1 & 2 | 2 | 5 | 5 | 5% | ECD 10/7/2023
8 | Meet with Customer to Provide Update | Milestone | TBD | 1 | 20 | 10 | 5% | ECD 10/9/23
9 | Determine Top 2 Vehicles VIa Driver Reports | Milestone | TBD | 1 | 15 | 7.5 | 5% | ECD 10/10/2023
10 | Prepare Report Outline Selection with photos | Milestone | TBD | 1 | 10 | 5 | 5% | ECD 10/10/2023
11 | Meet with customer to GIve Top 2 Vehicles | Milestone | TBD | 1 | 10 | 5 | 5% | ECD 10/10/2023
12 | Invoice Customer | Milestone | TBD | 1 | 10 | 5 | 5% | ECD 10/11/23
13 | Customer Feedback | Milestone | TBD | 1 | 5 | 2.5 | 5% | ECD 10/11/23
14 | Update Internal Documents | Milestone | TBD | 1 | 20 | 10 | 5% | ECD 10/11/23
1042.5
To add more data, Insert new rows ABOVE this one

## Dark
PROJECT: Dark
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Gupreet Bawa
Project start date: | 2023-09-26 |  |  |  |  | October | [34 empty] | November
Scrolling increment: | 5 | time axis 2023-10-01 to 2023-11-25
Milestone description | Category | Assigned to | Progress | Start | Days | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
TITLE 1
Task 1 | Goal | Name | 25% | 2023-09-26 | 3
Task 2 | Milestone |  |  | 2023-10-01 | 1 | bar: S
Task 3 | Low Risk |  | 50% | 2023-09-23 | 10
Task 4 | Milestone |  |  | 2023-10-16 | 1 | bar: M
Task 5 | Med Risk |  | 10% | 2023-10-02 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2023-10-02 | 13
Task 2 | On Track |  | 50% | 2023-10-04 | 9
Task 3 | Low Risk |  | 33% | 2023-10-09 | 11
Task 4 | Milestone |  |  | 2023-10-11 | 1 | bar: W
Task 5 |  |  |  | 2023-10-12 | 24
TITLE 3
Task 1 | On Track |  |  | 2023-10-11 | 4
Task 2 | Med Risk |  |  | 2023-10-14 | 14
Task 3 | On Track |  |  | 2023-10-29 | 6
Task 4 | Goal |  |  | 2023-11-02 | 3 | T: 2; F: 2; S: 2
Task 5 | Low Risk |  |  | 2023-10-02 | 19
TITLE 4
Task 1 |  |  |  | 2023-11-05 | 15
Task 2 |  |  |  | 2023-11-19 | 5
Task 3 | Milestone |  |  | 2023-12-31 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT: Color
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Hayden Cook
Project start date: | 2023-09-26 |  |  |  |  | October | [34 empty] | November
Scrolling increment: | 5 | time axis 2023-10-01 to 2023-11-25
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2023-10-01 to 2023-11-25
TITLE 1
Task 1 | Goal | Name | 25% | 2023-09-26 | 3
Task 2 | Milestone |  |  | 2023-10-01 | 1 | bar: 2023-10-01
Task 3 | Low Risk |  | 50% | 2023-09-23 | 10
Task 4 | Milestone |  |  | 2023-10-16 | 1 | bar: 2023-10-16
Task 5 | Med Risk |  | 10% | 2023-10-02 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2023-10-02 | 13
Task 2 | On Track |  | 50% | 2023-10-04 | 9
Task 3 | Low Risk |  | 33% | 2023-10-09 | 11
Task 4 | Milestone |  |  | 2023-10-11 | 1 | bar: 2023-10-11
Task 5 |  |  |  | 2023-10-12 | 24
TITLE 3
Task 1 | On Track |  |  | 2023-10-11 | 4
Task 2 | Med Risk |  |  | 2023-10-14 | 14
Task 3 | On Track |  |  | 2023-10-29 | 6
Task 4 | Goal |  |  | 2023-11-02 | 3 | 2023-11-02: 2; 2023-11-03: 2; 2023-11-04: 2
Task 5 | Low Risk |  |  | 2023-10-02 | 19
TITLE 4
Task 1 |  |  |  | 2023-11-05 | 15
Task 2 |  |  |  | 2023-11-19 | 5
Task 3 | Milestone |  |  | 2023-12-31 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one